## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | Set up the Flask-based project structure and session configuration for the customer support coaching application. | Must Have |  |  | 3- Completed
1 | 1 | US02 | Develop the Customer Simulator Agent to generate realistic customer messages based on scenario, persona, difficulty and language. | Must Have | US01 |  | 3- Completed
1 | 1 | US03 | Implement intent, sentiment and frustration analysis for incoming customer messages. | Must Have | US01 |  | 3- Completed
2 | 2 | US04 | Build the multi-agent orchestration flow for analysis, response evaluation, coaching and escalation monitoring. | Must Have | US02, US03 |  | 3- Completed
2 | 2 | US05 | Implement session management to maintain conversation history, analysis results and coaching data across multiple turns. | Must Have | US04 |  | 3- Completed
3 | 3 | US06 | Build the knowledge base and RAG workflow for retrieving relevant support information during customer interactions. | Must Have | US04 |  | 3- Completed
3 | 3 | US07 | Integrate knowledge recommendations and live AI response guidance into the coaching interface. | Must Have | US06 |  | 3- Completed
4 | 4 | US08 | Implement Simulator, Manual and Replay interaction modes and connect them with the session workflow. | Must Have | US05, US07 |  | 3- Completed
4 | 4 | US09 | Generate a post-interaction report with performance scores, strengths, improvement areas and coaching recommendations. | Should Have | US08 |  | 3- Completed
4 | 4 | US10 | Develop performance analytics to track completed sessions, performance trends, escalation triggers and knowledge gaps. | Should Have | US09 |  | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT SPRINT BACKLOG
US01 | T01 | Create Flask project structure, routes and session configuration. | Jul 9th | Jul 11th |  | Coding | 3- Completed | 6
US02 | T02 | Implement Customer Simulator Agent and Gemini-based customer message generation. | Jul 10th | Jul 15th |  | Coding | 3- Completed | 10
US03 | T03 | Implement intent, sentiment and frustration analysis for customer messages. | Jul 12th | Jul 15th |  | Coding | 3- Completed | 8
US04 | T04 | Integrate specialized agents through the orchestrator and coaching pipeline. | Jul 16th | Jul 22nd |  | Integration | 3- Completed | 10
US05 | T05 | Implement multi-turn session management and conversation history handling. | Jul 20th | Jul 29th |  | Coding | 3- Completed | 8
US06 | T06 | Prepare support knowledge, chunk content and implement RAG-based retrieval. | Jul 30th | Aug 5th |  | Coding | 3- Completed | 12
US07 | T07 | Integrate knowledge recommendations and live suggested responses into the frontend. | Aug 3rd | Aug 12th |  | Integration | 3- Completed | 10
US08 | T08 | Complete Simulator and Manual interaction flows with correct session routing. | Aug 13th | Aug 16th |  | Coding | 3- Completed | 8
US08 | T09 | Implement Replay Mode with transcript upload and replay processing. | Aug 15th | Aug 18th |  | Coding | 3- Completed | 8
US09 | T10 | Implement post-interaction summary and detailed performance report. | Aug 16th | Aug 19th |  | Coding | 3- Completed | 8
US10 | T11 | Develop performance analytics for session trends, improvement indicators and escalation triggers. | Aug 17th | Aug 20th |  | Coding | 3- Completed | 10
US10 | T12 | Perform end-to-end testing, fix integration issues and finalize the application. | Aug 19th | Aug 20th |  | Testing | 3- Completed | 8

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | Jul 11th | Initial project setup and Gemini integration required correct environment and API configuration. | Configured the virtual environment, project structure and AI client, then continued simulator and analysis development.
2 | Jul 22nd | Multi-agent outputs and conversation state had to remain consistent across multiple turns. | Integrated agents through the orchestrator and improved session management for conversation history and coaching data.
3 | Aug 5th | Knowledge retrieval had to return relevant support information and connect correctly with the coaching UI. | Prepared the knowledge base, implemented retrieval flow and integrated knowledge recommendations with live guidance.
4 | Aug 18th | Mode switching, report navigation and analytics needed final integration and testing. | Completed Simulator, Manual and Replay flows, fixed session routing, added reports and analytics, and performed end-to-end testing.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | Jul 9th | Jul 15th |  | Build the core simulator and customer analysis modules. | Relying on incomplete environment configuration. | Testing each module after implementation. | Configured the environment correctly and completed the initial AI interaction workflow.
2 | 2 | Jul 16th | Jul 29th |  | Integrate the specialized agents and maintain multi-turn session state. | Handling agent outputs independently without a common session flow. | Using modular agent responsibilities and incremental testing. | Centralized the workflow through the orchestrator and improved session management.
3 | 3 | Jul 30th | Aug 12th |  | Build the knowledge retrieval workflow and connect it with live coaching. | Using generic guidance when relevant knowledge is available. | Keeping the knowledge base modular and reusable. | Integrated RAG-based knowledge recommendations with the coaching interface.
4 | 4 | Aug 13th | Aug 20th |  | Complete all interaction modes, reports, analytics and final testing. | Mixing mode-specific state and navigation between sessions. | End-to-end testing and fixing issues before finalizing features. | Separated Simulator, Manual and Replay flows, completed reporting and analytics, and finalized the application.