## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sarvani | Jul 11th | Application startup was delayed while loading Google GenAI dependencies and SSL context. | 1 | Sarvani | Others | Activated the correct virtual environment, verified installed packages and reran the Flask application after environment initialization. | Jul 11th | Closed | Application started successfully after environment setup.
2 | Sarvani | Jul 15th | Frontend displayed undefined analysis values because the API response stored intent, sentiment and frustration inside the analysis object. | 1 | Sarvani | Logical | Updated frontend response handling to read values from the correct analysis object returned by the backend. | Jul 15th | Closed | Intent, sentiment and frustration values displayed correctly.
3 | Sarvani | Jul 22nd | Conversation state and outputs from multiple agents were not consistently coordinated during a complete turn. | 2 | Sarvani | Logical | Centralized the turn workflow in AgentOrchestrator and passed analysis, knowledge, evaluation, coaching and escalation results through one process. | Jul 22nd | Closed | Multi-agent turn processing became consistent.
4 | Sarvani | Jul 29th | Current customer message and previous escalation score were not reliably maintained between conversation turns. | 2 | Sarvani | Logical | Updated session management and route logic to store the current customer message, conversation history and escalation score for each session. | Jul 29th | Closed | Multi-turn session continuity worked correctly.
5 | Sarvani | Aug 5th | Knowledge retrieval had to support different knowledge-agent method signatures during integration. | 3 | Sarvani | Maintainability | Added a reusable knowledge retrieval helper with safe fallback handling for supported method signatures and errors. | Aug 5th | Closed | Knowledge retrieval integrated without breaking the coaching flow.
6 | Sarvani | Aug 12th | AI suggested replies and retrieved knowledge were not fully connected to the live coaching interface. | 3 | Sarvani | Logical | Integrated customer analysis and knowledge retrieval with the coaching agent's suggested-response endpoint. | Aug 12th | Closed | Live response guidance returned relevant suggestions.
7 | Sarvani | Aug 16th | Starting a new Manual session after using Simulator Mode could continue inside the previous simulator flow. | 4 | Sarvani | Logical | Separated interaction-mode handling, stored the selected mode in session data and updated frontend routing/session initialization. | Aug 16th | Closed | Simulator and Manual sessions now start with their correct mode behavior.
8 | Sarvani | Aug 18th | Replay Mode required transcript upload and replay-specific processing instead of normal simulator message generation. | 4 | Sarvani | Logical | Implemented Replay Mode handling for uploaded transcript content and connected it to the coaching session workflow. | Aug 18th | Closed | Replay transcript flow tested successfully.
9 | Sarvani | Aug 19th | Post-interaction report page initially did not show the required session performance information correctly. | 4 | Sarvani | User Interface | Connected the report page to session report data and added performance scores, outcome, strengths, improvement areas and recommendations. | Aug 19th | Closed | Completed sessions now display the detailed report.
10 | Sarvani | Aug 20th | Dashboard navigation did not initially expose all interaction modes and performance analytics clearly. | 4 | Sarvani | User Interface | Updated dashboard navigation and templates to provide access to Simulator, Manual, Replay and Analytics features. | Aug 20th | Closed | Navigation and analytics access verified during final testing.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others